## Sheet1
Number | Section | sectionDescription | Description
1 |  |  | Review unresolved issues on the design development checklist
2 |  |  | Periodically review internal office budgets and production schedules; compare with actual progress
3 |  |  | Review and update schedule of completion dates for this and all subsequent phases - Inform the project team and owners of any revisions
4 |  |  | Establish a clear chain of command and response for the construction document phase
5 |  |  | Review and update staff time and production cost projections- adjust the number and type of staff as required
6 |  |  | Review and update staff time and production cost projections- distribute updated project schedule to owner project staff and consultants
7 |  |  | Schedule training sessions for personnel who are not experienced in applicable production methods
8 |  |  | Updated and distribute project directory
9 |  |  | Identify all documents with project number and date
10 |  |  | As documents develop, confer with and obtain further review from the regulatory agencies such as - building department
11 |  |  | As documents develop, confer with and obtain further review from the regulatory agencies such as - fire marshal
12 |  |  | As documents develop, confer with and obtain further review from the regulatory agencies such as - dept. of health
13 |  |  | As documents develop, confer with and obtain further review from the regulatory agencies such as - dept. of education
14 |  |  | As documents develop, confer with and obtain further review from the regulatory agencies such as - other
15 |  |  | Check with the applicable regulatory agencies and establish schedule for submission and/or review
16 |  |  | Coordinate the work of all team members, including consultants
17 |  |  | Coordinate drawings with project manual
18 |  |  | Update preliminary construction cost estimate and advise the owner of any changes
19 |  |  | Submit monthly or periodic invoice to owner for payment, include reimbursable expenses
20 |  |  | Review the program and verify compliance
21 |  |  | Re-check design development documents for code compliance
22 |  |  | Develop a list of required drawings; check requirements of the owner and governing bodies
23 |  |  | Prepare a one-fourth size mock-up of all project drawings, their sequence, and the information to appear on each sheet - distribute copies to concerned parties for review, then distribute final copies to all staff as a supervisory guide
24 |  |  | Determine the final printing system
25 |  |  | Determine the specific drafting systems appropriate to parts or all of the project and include them in the mock-up set- computer text and/or graphics
26 |  |  | Determine the specific drafting systems appropriate to parts or all of the project and include them in the mock-up set- manual drafting
27 |  |  | Determine the specific drafting systems appropriate to parts or all of the project and include them in the mock-up set- photo drafting
28 |  |  | Determine the specific drafting systems appropriate to parts or all of the project and include them in the mock-up set- overlay drafting
29 |  |  | Determine the specific drafting systems appropriate to parts or all of the project and include them in the mock-up set- keynotes
30 |  |  | Determine the specific drafting systems appropriate to parts or all of the project and include them in the mock-up set- linked notes and/or details with CSI numbers
31 |  |  | Determine the specific drafting systems appropriate to parts or all of the project and include them in the mock-up set- full sheets of reusable standard or typical file data
32 |  |  | Determine the specific drafting systems appropriate to parts or all of the project and include them in the mock-up set- paste-up
33 |  |  | Review the completed working drawing index with all concerned parties - obtain feedback and make revisions as necessary
34 |  |  | Determine the completion date of the limited architectural floor plan base sheet for the consultant's use
35 |  |  | Develop title block format (check requirements of owner, licensing laws and governing bodies)
36 |  |  | Develop format for door, window and finish schedules
37 |  |  | Establish a checklist and timetable for the client's applications for approvals and permits from governing bodies
38 |  |  | If applicable, determine alternates cash allowances and unit prices
39 |  |  | Obtain owners instructions on insurance, bonds, construction agreements and bidding procedures
40 |  |  | Submit copies of general and supplementary conditions for owners review or obtain owner's specific contract requirements
41 |  |  | Determine what items, if any, are to be furnished by the owner and those items not to be included in the contract
42 |  |  | Verify owner's acceptance of the proposed designs for mechanical and electrical systems
43 |  |  | Monitor approval and permit process
44 |  |  | Obtain schedule for delivery and installation of owner-furnished materials
45 |  |  | Assemble final drawings and specifications for coordination
46 |  |  | Conduct team meetings to resolve coordination issues
47 |  |  | Revise documents as required
48 |  |  | If project will be bid, assemble bidding documents
49 |  |  | Determine whether prevailing wage statutes apply in project jurisdiction
50 |  |  | Prepare final calculations of net and gross areas and volumes
51 |  |  | Obtain each consultant's final construction cost estimate for their portion of the project
52 |  |  | Prepare final construction cost estimate
53 |  |  | Prepare testing and quality control program budgets and assist owner in selection of testing agency
54 |  |  | Submit drawings, project manual, construction cost estimate and area calculations to the owner
55 |  |  | Obtain and review qualification statements from interested bidders
56 |  |  | Place architect's and engineer's seals on the documents and obtain signatures required by reviewing authorities
57 |  |  | Assist owner in filing documents for final approvals and permits
58 |  |  | Obtain owner's written authorization to proceed to the bidding or negation phase