## Sheet1
Number | Section | SectionDescription | Description
1 |  |  | Review unresolved issues on schematic design checklist
2 |  |  | Periodically review internal office budgets and production schedules; compare with actual progress- review and update schedule of completion dates for this and all subsequent phases
3 |  |  | Periodically review internal office budgets and production schedules; compare with actual progress - review and update staff time and production schedules; compare with actual progress
4 |  |  | Periodically review internal office budgets and production schedules; compare with actual progress- adjust number and type of staff as required
5 |  |  | Periodically review internal office budgets and production schedules; compare with actual progress - distribute updated project schedule to owner, staff, and consultants
6 |  |  | Periodically review internal office budgets and production schedules; compare with actual progress - update and distribute project directory
7 |  |  | As documents develop, confer with and obtain preliminary review from regulatory agencies such as - building department
8 |  |  | As documents develop, confer with and obtain preliminary review from regulatory agencies such as - fire marshal (state & local)
9 |  |  | As documents develop, confer with and obtain preliminary review from regulatory agencies such as - dept. of health
10 |  |  | As documents develop, confer with and obtain preliminary review from regulatory agencies such as - dept. of education
11 |  |  | As documents develop, confer with and obtain preliminary review from regulatory agencies such as - zoning commission
12 |  |  | As documents develop, confer with and obtain preliminary review from regulatory agencies such as - planning commission
13 |  |  | As documents develop, confer with and obtain preliminary review from regulatory agencies such as - design review board
14 |  |  | As documents develop, confer with and obtain preliminary review from regulatory agencies such as - other
15 |  |  | Identify all documents with project number and date
16 |  |  | Submit monthly or periodic invoice to the owner for payment; include reimbursable expenses
17 |  |  | Obtain owner's approval for expenditures for any models, perspectives or renderings required for the project
18 |  |  | Review the building design program and verify compliance
19 |  |  | Re-check schematic design documents for code compliance
20 |  |  | Obtain owner's approval in the event that additional consultants are required
21 |  |  | Receive results of all investigations and tests, including soil borings and analysis - If necessary, request additional information - forward final information to appropriate consultants
22 |  |  | Review all other data received from the owner and consultants
23 |  |  | Obtain owner's standards and requirements
24 |  |  | In consultation with the owner and consultants, develop a checklist of special systems
25 |  |  | Define actual occupancy for each area, check against program, and forward to consultants
26 |  |  | Request that the structural engineer investigate and report on their review of applicable regulations
27 |  |  | Request that the mechanical and electrical engineers - contact utility companies and public authorities for all services and initiate approval process
28 |  |  | Request that the mechanical and electrical engineers - investigate and report on their review of all applicable local, public and utility regulations
29 |  |  | Request that the mechanical and electrical engineers - notify the architect of space and location requirements for systems
30 |  |  | Request that the mechanical and electrical engineers - prepare estimates of probable operating costs with recommendations for implementation
31 |  |  | Review engineers' estimates of probable operating costs and forward to owner - obtain owner's approval for the selected fuel sources
32 |  |  | Prepare site plan indicating building location and site improvements
33 |  |  | Prepare other necessary documents to include plans, elevations, sections, schedules and notes
34 |  |  | Prepare area calculations (net and gross)
35 |  |  | Prepare building volume calculations
36 |  |  | Prepare a preliminary project manual
37 |  |  | Update materials, equipment, fixtures and building systems file
38 |  |  | Direct consultants to prepare design documents as required to illustrate and describe their portions of the project
39 |  |  | Require all consultants to produce their design documents following the same format as the architectural drawings
40 |  |  | Conduct one or more group coordination meetings with consultants
41 |  |  | Reach agreement on structural, mechanical, electrical and other building systems
42 |  |  | Confirm that the selected engineering and construction systems are compatible
43 |  |  | Direct consultants to provide preliminary construction cost estimates for their portion of the project
44 |  |  | Update the statement of probable construction cost - If specifically requested by owner, provide a detailed cost estimate as an additional service
45 |  |  | Submit design development documents
46 |  |  | Plan and prepare appropriate presentation materials
47 |  |  | After presentation, identify changes, repercussions, contradictions, or conflicts and discuss with owner
48 |  |  | Confirm with the owner which contracting procedure will be used
49 |  |  | Obtain owner's written approval of design development documents
50 |  |  | Obtain owner's written authorization to proceed to construction documents phase