## Sheet1
Number | Section | SectionDescription | Description
1 |  |  | Verify your ability to meet the professional liability insurance and licensing requirements of the project locality
2 |  |  | Determine the basis of services- basic services agreement
3 |  |  | Determine the basis of services- designated services agreement
4 |  |  | Determine the basis of services- interior design service agreement
5 |  |  | Determine the basis of services- construction management agreement
6 |  |  | Determine the basis of services- design/build agreement
7 |  |  | Determine what constitutes additional or supplemental services if basic services agreement is used
8 |  |  | Determine designated services based on AIA Document B163, if applicable
9 |  |  | Ascertain method for award of construction contraction- direct selection
10 |  |  | Ascertain method for award of construction contraction- competitive bidding (open or closed)
11 |  |  | Ascertain method for award of construction contraction- negotiated
12 |  |  | Ascertain method for award of construction contraction- single-prime
13 |  |  | Ascertain method for award of construction contraction- multiple prime
14 |  |  | Ascertain method for award of construction contraction- construction management
15 |  |  | Ascertain method for award of construction contraction- design/build
16 |  |  | Review program requirements with the owner
17 |  |  | Determine owner's time schedule for bidding and occupancy
18 |  |  | Determine owner's budget (e.g., cost estimate, available funds, fixed limit of construction cost, etc).
19 |  |  | Determine whether project budget, schedule and program objectives are compatible and realistic
20 |  |  | Determine the compensation method for all services
21 |  |  | Select and organize the design team, including structural, mechanical, electrical and special consultants
22 |  |  | Inquire regarding consultants' ability to meet time schedule, liability insurance and licensing requirements; determine compensation
23 |  |  | Prepare project estimating and budget worksheet- time required for services
24 |  |  | Prepare project estimating and budget worksheet- personnel time and production cost projections
25 |  |  | Prepare project estimating and budget worksheet- cost of basic services for entire project
26 |  |  | Prepare project estimating and budget worksheet- cost of contemplated additional services
27 |  |  | Prepare project estimating and budget worksheet- compensation for additional services
28 |  |  | Prepare project estimating and budget worksheet-estimate of reimbursable expenses
29 |  |  | Prepare project estimating and budget worksheet- cost of special insurance
30 |  |  | Prepare project estimating and budget worksheet- other costs (consultants, etc.)
31 |  |  | Verify form of general conditions to be used
32 |  |  | Prepare owner/architect agreement form and submit to owner
33 |  |  | Have legal and insurance counsel review any modifications or specific provisions required by owner
34 |  |  | Verify that the office has the means, space, equipment, and personnel capabilities required to complete the project - conflicts with other projects
35 |  |  | Verify that the office has the means, space, equipment, and personnel capabilities required to complete the project - new hiring
36 |  |  | Verify that the office has the means, space, equipment, and personnel capabilities required to complete the project - expansion
37 |  |  | Verify that the office has the means, space, equipment, and personnel capabilities required to complete the project - joint venture
38 |  |  | Verify that the office has the means, space, equipment, and personnel capabilities required to complete the project - branch office
39 |  |  | Review final agreement with legal and insurance counsel- approve any modifications made by owner or renegotiate
40 |  |  | Prepare three originals for signature, complete execution of the agreement and schedule or initiate the first formal phase of work
41 |  |  | Submit initial invoice to owner, if applicable, include reimbursable expenses
42 |  |  | Submit information required by the agreement
43 |  |  | Distribute executed originals and copies of the final agreement to the appropriate parties
44 |  |  | Assign a project number