## Sheet1
Number | Section | SectionDescription | Description
1 |  |  | Periodically review internal office budgets and production schedules; compare with actual progress
2 |  |  | Submit monthly or periodic invoices to the owner for payment; include reimbursable expenses
3 |  |  | Obtain the name of the owner's authorized representative
4 |  |  | Update and distribute project directory
5 |  |  | Assign staff to the project
6 |  |  | Distribute project schedule to owner, project staff, and consultants
7 |  |  | Review all data furnished, including building design program, budget, project budget, legal, site, code, space and special owner requirements
8 |  |  | Prepare functional space plans
9 |  |  | Provide engineers and consultants with pertinent program data and functional space plans
10 |  |  | Analyze comparative systems with engineers and consultants; select systems to be used in the project - structural
11 |  |  | Analyze comparative systems with engineers and consultants; select systems to be used in the project - mechanical
12 |  |  | Analyze comparative systems with engineers and consultants; select systems to be used in the project - electrical
13 |  |  | Analyze comparative systems with engineers and consultants; select systems to be used in the project - other consultants
14 |  |  | Require all consultants to produce their schematic plans following the same format, scale, and drawing positions as the architectural drawings
15 |  |  | Create or obtain lists of special building equipment and fixtures required by the owner that may affect the consultant's work; distribute the lists to appropriate consultants
16 |  |  | Review architectural schematic diagrams with consultants
17 |  |  | Confirm that the selected engineering and construction services are compatible with one another
18 |  |  | Prepare schematic design documents to include - site plan with diagrammatic indications showing vertical relationships
19 |  |  | Prepare schematic design documents to include - sections through the site showing horizontal relationship
20 |  |  | Prepare schematic design documents to include - principal floor plans
21 |  |  | Prepare schematic design documents to include - general descriptive views or elevations
22 |  |  | Prepare schematic design documents to include - illustrative sketches, models or renderings, if required
23 |  |  | Calculate areas and volumes, and analyze plan efficiency of the design by usable area, area per person or other method
24 |  |  | Prepare a general description of the project, including materials and equipment outlines
25 |  |  | Begin research on materials, equipment fixtures and building systems
26 |  |  | Start project outline specifications
27 |  |  | Obtain and review statements of probable construction cost from each consultant
28 |  |  | Prepare an estimate of probable construction cost based on all available data
29 |  |  | Select construction cost estimating system - square foot unit cost
30 |  |  | Select construction cost estimating system - square foot cost according to building type
31 |  |  | Select construction cost estimating system - volume unit cost
32 |  |  | Select construction cost estimating system - systems estimate
33 |  |  | Select construction cost estimating system - quantity survey
34 |  |  | Submit schematic design documents to the owner
35 |  |  | Plan appropriate presentation media
36 |  |  | Prepare presentation of optional design features and variations
37 |  |  | After presentation, evaluate changes and comments
38 |  |  | Document revisions to scope of the work and review with owner
39 |  |  | Obtain owner's written authority of schematic design documents
40 |  |  | Obtain owner's written authority to proceed to the design development phase