## Sheet1
Number | Section | SectionDescription | Description
1 |  |  | Review unresolved issues from bidding or negotiation phase
2 |  |  | Update project directory
3 |  |  | Review and update project schedule
4 |  |  | Develop and implement a system of routing and distribution for project correspondence and submittals
5 |  |  | Create construction contract administration files to include - correspondence and meeting reports
6 |  |  | Create construction contract administration files to include - schedules
7 |  |  | Create construction contract administration files to include - field reports
8 |  |  | Create construction contract administration files to include - project photography
9 |  |  | Create construction contract administration files to include - phone log
10 |  |  | Create construction contract administration files to include - requests for information (RFI's)
11 |  |  | Create construction contract administration files to include - construction change directives (CCD's)
12 |  |  | Create construction contract administration files to include - requests for proposals (RFP's)
13 |  |  | Create construction contract administration files to include - change orders
14 |  |  | Create construction contract administration files to include - supplemental instructions
15 |  |  | Create construction contract administration files to include - quality control reports
16 |  |  | Create construction contract administration files to include - submittals
17 |  |  | Create construction contract administration files to include - agency inspections, permits and approvals
18 |  |  | Create construction contract administration files to include - applications for payment
19 |  |  | Create construction contract administration files to include - owner-architect agreement
20 |  |  | Create construction contract administration files to include - owner-contractor agreement
21 |  |  | Create construction contract administration files to include - consultant agreement
22 |  |  | Create construction contract administration files to include - schedule of values
23 |  |  | Create construction contract administration files to include - observations of contractor performance
24 |  |  | Create construction contract administration files to include - certificates of insurance
25 |  |  | Create construction contract administration files to include - property insurance policy
26 |  |  | Create construction contract administration files to include - contract bonds
27 |  |  | Create construction contract administration files to include - project closeout
28 |  |  | Assign contract administration and site observation responsibilities
29 |  |  | With the owner, review and approve or take other appropriate action on contractor's list of subcontractors and suppliers
30 |  |  | Notify the consultants of selected prime contractors and subcontractors
31 |  |  | Obtain and review contractor's submittal schedule
32 |  |  | Establish a time for preconstruction meeting
33 |  |  | Establish a site observation and project meeting schedules; coordinate with agency inspection requirements
34 |  |  | If required, notify the owner to submit applications for permanent gas, electric, water, telephone, and other services
35 |  |  | Have owner file a copy of all property insurance polices with contractor
36 |  |  | If the owner does not intend to purchase property insurance, have owner notify contractor in writing - if the contractor elects to purchase such insurance, initiate appropriate change order
37 |  |  | Review construction budget (including contingencies) with the owner
38 |  |  | Review owner - supplied labor and materials
39 |  |  | If required, send the notice to proceed to the contractor
40 |  |  | Keep owner informed on the progress of work - prepare a field report for each visit to the site
41 |  |  | Obtain and review the contractor's updated progress schedule and advise the owner of potential revisions to anticipated occupancy date
42 |  |  | Prior to the first application for payment, receive, review, and approve, if appropriate, contractor's schedule of values
43 |  |  | Receive and review the contractor's application for payment; respond appropriately
44 |  |  | Verify requirements, if any, for reduction in retainage and have contractor submit consent of surety documentation
45 |  |  | Submit monthly or periodic invoice to the owner for payment; include reimbursable expenses
46 |  |  | List tests required for the project and note their approximate dates in accordance with current construction schedule
47 |  |  | Obtain and review required test reports
48 |  |  | Receive submittals; review, take appropriate action, and return to the contractor
49 |  |  | Maintain submittal log
50 |  |  | Review contractor's proposed cost for changes and respond appropriately
51 |  |  | Receive from the contractor notification of substantial completion and list of items to be completed or corrected
52 |  |  | Inspect the project to confirm substantial completion
53 |  |  | Respond to the contractor's punchlist of remaining work to be repaired or completed
54 |  |  | If applicable, review contractor's request for a reduction of retainage
55 |  |  | When the project is judged to be substantially complete, prepare a certificate of substantial completion
56 |  |  | If reproducible record drawings are required, provide the contractor with appropriate media
57 |  |  | Request that the contractor submit project close-out documents
58 |  |  | Review the close-out submittals for completeness
59 |  |  | Verify that the contractor has obtained a certificate of occupancy or occupancy permit
60 |  |  | Review the contractor's request for final inspection and conduct a field inspection of the project to confirm completion
61 |  |  | Prepare a final field inspection report
62 |  |  | Review the contractor's application for final payment, including required attachments such as waivers of lien and consent of surety documentation
63 |  |  | Issue a final certificate for payment
64 |  |  | Submit (final) monthly or periodic invoice to the owner for payment, include reimbursable expenses
65 |  |  | Assemble and file for future reference complete project and cost records for both construction and professional services
66 |  |  | Archive project information and materials according to type; indicate duration for archival retention (prior to discard)
67 |  |  | Prior to expiration of the one-year period of corrections, obtain the owner's authorization to conduct an inspection to determine if any work is required by the contractor to remedy defects