## Sheet1
Number | Section | SectionDescription | Description
1 |  |  | Review unresolved issues from construction documents phase
2 |  |  | Review and update project schedule
3 |  |  | Investigate whether other major projects have concurrent bid dates, or if other factors require bid modification
4 |  |  | Consult with the owner's legal counsel on the existence of any special laws regarding the bidding process, construction documents and forms of agreement
5 |  |  | Identify the architect's and the owner's respective responsibilities advertising for bids, receiving bids, bid evaluation and negotiation
6 |  |  | For open bidding, publish advertisement for bids (in some cases, owner may publish) if separate prime contracts are to be awarded, separate advertisements may be necessary
7 |  |  | Obtain and review qualification statements from interested bidders
8 |  |  | For bidding by invitation, notify selected bidders
9 |  |  | If the construction contract is based on negotiation, assist the owner in negotiating with prospective contractor
10 |  |  | Prepare register of bid documents
11 |  |  | Distribute bidding documents to bidders and obtain deposits
12 |  |  | Issue documents to plan rooms
13 |  |  | Hold a pre-bid conference, prepare a report and distribute copies
14 |  |  | Record responses to bidders' requests for clarification in the form of a written addendum distributed to all bidders
15 |  |  | Upon return of documents, refund bid security to bidders who either withdraw or are disqualified
16 |  |  | Evaluate proposed substitutions and requests for product approval; notify bidders of accepted substitutions by addendum
17 |  |  | Confirm participation of prospective bidders
18 |  |  | Prepare a bid tabulation form
19 |  |  | Assist the owner in the receipt, tabulation and analysis of bids; check bids for irregularities
20 |  |  | Advise the owner on selection of alternates and obtain owner's approval
21 |  |  | Assist the owner in the process of acceptance or rejection of bids
22 |  |  | Notify bidders of acceptance or rejection; obtain return of bidding documents from unsuccessful bidders; return their deposits and bid securities
23 |  |  | Request and receive submission of post-bid information
24 |  |  | Assist owner's legal counsel in preparation of construction contract - if separate prime contracts are awarded, obtain assistance of consultants
25 |  |  | Schedule times for confirmation of required owner and contractor insurance coverage
26 |  |  | Obtain from the contractor performance bonds, labor and material payment bonds, and any contract bonds required by statute - review and forward copies of bonds to owner
27 |  |  | Obtain the contractor's certificate of insurance - review and forward copies of the certificate to the owner
28 |  |  | Obtain a copy of the property insurance policy from the party responsible for obtaining such coverage - review and forward copies to the other party
29 |  |  | Identify and review any atypical insurance arrangements between the owner and contractor - include descriptions of such arrangements in the contract
30 |  |  | Assist the owner in preparing and sending to the contractor notices to proceed with the work
31 |  |  | Provide the contractor with all necessary contract documents
32 |  |  | Obtain owner's written approval to proceed with construction contract administration phase
33 |  |  | Submit monthly or periodic invoices to the owner for payment; include reimbursable expenses