## Sheet1
Number | Section | SectionDescription | Description
1 | 01 | Preconstruction Phase | Check overall CM Responsibilities
2 | 01 | Preconstruction Phase | Review project program
3 | 01 | Preconstruction Phase | Provide preliminary evaluation - owner's program
4 | 01 | Preconstruction Phase | Provide preliminary evaluation - project schedule
5 | 01 | Preconstruction Phase | Provide preliminary evaluation - construction budget
6 | 01 | Preconstruction Phase | Prepare or assist in preparing a preliminary cost estimate
7 | 01 | Preconstruction Phase | Provide cost evaluations for alternative materials and systems
8 | 01 | Preconstruction Phase | Advise project architect - proposed site use
9 | 01 | Preconstruction Phase | Advise project architect - selections of materials
10 | 01 | Preconstruction Phase | Advise project architect - building systems and equipment
11 | 01 | Preconstruction Phase | Advise project architect - availability of materials and labor
12 | 01 | Preconstruction Phase | Advise project architect - time requirements for procurement, installation, and construction
13 | 01 | Preconstruction Phase | Advise project architect - possible economies
14 | 01 | Preconstruction Phase | Update project schedule
15 | 01 | Preconstruction Phase | Update cost estimate - schematic design phase
16 | 01 | Preconstruction Phase | Update cost estimate - design development phase
17 | 01 | Preconstruction Phase | Update cost estimate - construction document phase
18 | 01 | Preconstruction Phase | Advise project architect regarding design details that might affect constructability, cost, and schedule
19 | 01 | Preconstruction Phase | Temporary project facilities - make recommendations to project
20 | 01 | Preconstruction Phase | Safety programs - provide owner with information regarding allocation of responsibilities, i.e., each contractor is responsible for safety
21 | 01 | Preconstruction Phase | Prepare list of bid packages
22 | 01 | Preconstruction Phase | Prepare construction schedule (include in specifications)
23 | 01 | Preconstruction Phase | Assist owner in selecting consultants and testing laboratories, if necessary
24 | 01 | Preconstruction Phase | Analyze labor availability and make recommendations
25 | 01 | Preconstruction Phase | Check requirements for equal opportunity employment and advise specifier
26 | 01 | Preconstruction Phase | Review specifications (assist in writing if needed)
27 | 01 | Preconstruction Phase | Prepare list of propective bidders for project architect's review
28 | 01 | Preconstruction Phase | Develp bidder's interest
29 | 01 | Preconstruction Phase | Conduct pre-bid conference, if necessary
30 | 01 | Preconstruction Phase | Receive bids (with project architect)
31 | 01 | Preconstruction Phase | Prepare bid tab
32 | 01 | Preconstruction Phase | With project architect, make recommendations to owner regarding acceptance or rejection of bids
33 | 01 | Preconstruction Phase | Prepare construction contracts and obtain contractor's and owner's signatures
34 | 01 | Preconstruction Phase | Obtain building permit
35 | 02 | Construction Phase | Return each contractor's copy of the construction contract with notice to proceed. Remind contractors of safety responsibility.
36 | 02 | Construction Phase | Hold preconstruction conference
37 | 02 | Construction Phase | Introduce owner, project architect, CM, contractors to project requirements - project description by project architect
38 | 02 | Construction Phase | Introduce owner, project architect, CM, contractors to project requirements - project goals by owner
39 | 02 | Construction Phase | Introduce owner, project architect, CM, contractors to project requirements - importance of construction schedule
40 | 02 | Construction Phase | Introduce owner, project architect, CM, contractors to project requirements - site conditions and materials storage
41 | 02 | Construction Phase | Introduce owner, project architect, CM, contractors to project requirements - temporary facilities
42 | 02 | Construction Phase | Application for payments - copies, submittal date, expect payment by, one approval copy will be returned to contractor
43 | 02 | Construction Phase | Prepare and distribute preconstruction meeting minutes to the owner, project architect, and all contractors
44 | 02 | Construction Phase | Materials and equipment delivery - all items needed in next 4-8 weeks
45 | 02 | Construction Phase | Inform parties that weekly progress meetings will be held
46 | 02 | Construction Phase | Prepare and send copies of progress meeting notes to owner, project architect, and each contractor
47 | 02 | Construction Phase | Maintain daily log
48 | 02 | Construction Phase | Process monthly applications for payment
49 | 02 | Construction Phase | Check shop drawings and monitor processing
50 | 02 | Construction Phase | Record actual progress on construction schedule
51 | 02 | Construction Phase | Ascertain whether contractor's maintain a clean and orderly job site
52 | 02 | Construction Phase | Maintain a set of construction documents at the job site
53 | 02 | Construction Phase | Mark up a set of construction documents for as-built documents
54 | 02 | Construction Phase | Assist owner with receiving, storage, and installation of owner-purchase equipment and/or furnishings
55 | 02 | Construction Phase | Observe on-site tests and testing of material, equipment, and systems
56 | 02 | Construction Phase | Prepare pre-final punchlist
57 | 02 | Construction Phase | With project architect, conduct final inspection
58 | 02 | Construction Phase | Secure copies of warranties and guarantees for the owner
59 | 02 | Construction Phase | Review final applications for payments
60 | 02 | Construction Phase | Turn over set of as-built documents to the owner