## Sheet1
Number | Section | SectionDescription | Description
1 |  |  | Survey stakes on property
2 |  |  | Lot cut and balanced/flat enough for proposed home/pad large enough for home
3 |  |  | Color sheet
4 |  |  | Copies of blueprints run
5 |  |  | Changes from Master Plan noted on blueprints
6 |  |  | Notice of Commencement affidavit or Certified Copy filed with county
7 |  |  | Permit sign up/NOC in box
8 |  |  | Utilities located
9 |  |  | Water meter ordered or well ordered to be installed
10 |  |  | Temporary power ordered if applicable/ check mailed to FPL if applicable/ call for pole to be placed
11 |  |  | Septic benchmark and finish floor height checked
12 |  |  | Order exterior doors
13 |  |  | Windows ordered
14 |  |  | Trusses ordered
15 |  |  | Slab electrical ordered
16 |  |  | Select subcontractors for foundation/slab stage
17 |  |  | Insurance certificate on file
18 |  |  | Verify plot plan is correct
19 |  |  | Order toilet
20 |  |  | Dumpster ordered (if space available)