## Sheet1
CostCode | CostCodeDescription | CostCodeQuantity | CostCodeUnit | Number | Description | Quantity | Unit | MatlConv | MatlUnit | MatlCostRate | LbrConv | LbrUnit | LbrBaseCostRate | LbrBurdenCostRate | EqpConv | EqpUnit | EqpBaseCostRate | EqpBurdenCostRate | SubConv | SubUnit | SubCostRate | OtherConv | OtherUnit | OtherCostRate
01 | Pre-Design | 1 | LS | 1 | Field Survey | 8 | Hrs. | 0 |  | 0 | 1 | Hrs. | 50 | 20 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
01 | Pre-Design | 1 | LS | 2 | Prepare Base Drawings | 12 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
01 | Pre-Design | 1 | LS | 3 | User Program Meeting | 8 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
02 | Schematic Design | 1 | LS | 4 | Dev/Confirm Plan and Elevations | 33 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
02 | Schematic Design | 1 | LS | 5 | User Review Meeting | 10 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
02 | Schematic Design | 1 | LS | 6 | Research Laboratory Equipment | 6 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
02 | Schematic Design | 1 | LS | 7 | Finish Selections | 22 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
02 | Schematic Design | 1 | LS | 8 | Presentation | 26 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
02 | Schematic Design | 1 | LS | 9 | Meeting Minutes and Administration | 22 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
03 | Design Development | 1 | LS | 10 | Outline Specifications | 9 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
03 | Design Development | 1 | LS | 11 | Backgrounds To Engineers | 6 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
03 | Design Development | 1 | LS | 12 | Engineering Mtg. Walkthru | 6 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
03 | Design Development | 1 | LS | 13 | Develop Special Details | 42 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
03 | Design Development | 1 | LS | 14 | Lab Lighting Design/Ceilings | 13 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
03 | Design Development | 1 | LS | 15 | Research Code Issues | 8 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
03 | Design Development | 1 | LS | 16 | Meeting Minutes and Administration | 21 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
04 | Construction Documents | 1 | LS | 17 | Construction Floor and Ceiling Plans | 32 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
04 | Construction Documents | 1 | LS | 18 | Elevation Drawings | 14 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
04 | Construction Documents | 1 | LS | 19 | Detail Sheets (CAD and Hand) | 26 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
04 | Construction Documents | 1 | LS | 20 | Detail Sheets (Skylight/Roof Hand) | 16 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
04 | Construction Documents | 1 | LS | 21 | Finishes Coordination | 24 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
04 | Construction Documents | 1 | LS | 22 | Symbols/Schedules/Notes | 20 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
04 | Construction Documents | 1 | LS | 23 | Landmark Submission | 4 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
04 | Construction Documents | 1 | LS | 24 | Building Department Submission | 20 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
04 | Construction Documents | 1 | LS | 25 | Specifications | 46 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
04 | Construction Documents | 1 | LS | 26 | Coordination/Consultants | 13 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
04 | Construction Documents | 1 | LS | 27 | Meetings and Minutes | 10 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
05 | Bid Phase | 1 | LS | 28 | Printing of Docs/Notices | 8 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
05 | Bid Phase | 1 | LS | 29 | Attend Pre-Bid Meeting | 6 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
05 | Bid Phase | 1 | LS | 30 | Clarifications/Addenda | 22 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
05 | Bid Phase | 1 | LS | 31 | Review Bids/Recommend | 18 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
06 | Pre-Construction Administration | 1 | LS | 32 | Site Visits / Meetings / Minutes | 12 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
06 | Pre-Construction Administration | 1 | LS | 33 | Shop Drawing Review | 56 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
07 | Construction Administration | 1 | LS | 34 | Site Visits / Meeting Minutes | 34 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
07 | Construction Administration | 1 | LS | 35 | Shop Drawing Review | 24 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0
07 | Construction Administration | 1 | LS | 36 | Punchlist | 10 | Hrs. | 0 |  | 0 | 1 | Hrs. | 70 | 0 | 0 |  | 0 | 0 | 1 |  | 0 | 1 |  | 0