## Sheet1
ProjectNumber | TaskDescription | TaskDueDate | TaskAuthorContact | TaskAssignedToContact | TaskPriority | TaskCategory | TaskStatus | TaskStatusDate | TaskPercentComplete
2016-02-Alden | Task1 | 2019-11-21 | Norman Wendl | Ben L. Schulz | Medium | Contract | Not Started |  | 0
2016-02-Alden | Lot Layout | 2019-11-21 | Norman Wendl | Gordon Hill | Medium | Drawing | Started |  | 10
2016-02-Alden | Dig | 2019-11-21 | Norman Wendl | Gordon Hill | Medium | Field | Waiting on Customer |  | 0
2016-02-Alden | Footers | 2019-11-22 | Ben L. Schulz | Gordon Hill | High | Procurement | Waiting on Vendor |  | 0
2016-02-Alden | Footer Inspection | 2019-12-05 | Ben L. Schulz | Gordon Hill | High | RFIs | On Hold |  | 20
2016-02-Alden | Pour Footer | 2019-12-05 | Ben L. Schulz | Gordon Hill | Low | Submittals | Completed
2016-02-Alden | Stock Block | 2019-12-05 | Maulik Oza | Norman Wendl | Low | Other |  |  | 0
2016-02-Alden | Foundation | 2019-12-06 | Maulik Oza | Norman Wendl |  | Contract |  |  | 0
2016-02-Alden | Cure Foundation | 2019-12-06 | Maulik Oza | Norman Wendl |  | Contract |  |  | 0

## Sheet3 (hidden)
TaskNumber | Description | ScheduledStartDate | Duration | Predecessor | ParentTask
1 | Foundation | 2013-01-01 | 0
2 | Lot Layout | 2013-01-07 | 1 |  | 1
3 | Dig | 2013-01-08 | 2 | 2 | 1
4 | Footers | 2013-01-10 | 5 | 3 | 1
5 | Footer Inspection | 2013-01-17 | 1 | 4 | 1
6 | Pour Footer | 2013-01-18 | 1 | 5 | 1
7 | Stock Block | 2013-01-21 | 1 | 6 | 1
8 | Foundation | 2013-01-22 | 7 | 7 | 1
9 | Cure Foundation | 2013-01-31 | 7 | 8 | 1
10 | Dampproof Foundation | 2013-01-31 | 3 | 8 | 1
11 | Brace Foundation | 2013-01-31 | 3 | 8 | 1
12 | Foundation Inspection | 2013-02-05 | 1 | 10 | 1
13 | Concrete Flatwork | 2013-02-06 | 3 | 12 | 1
14 | Backfill | 2013-02-11 | 3 | 9 | 1
15 | Enclosure | 2013-01-01 | 0
16 | Framing | 2013-02-14 | 10 | 14 | 15
17 | Construction Manager Inspection | 2013-02-28 | 1 | 16 | 15
18 | Roofing | 2013-03-01 | 4 | 17 | 15
19 | Siding | 2013-03-12 | 7 | 20 | 15
20 | Wall Insulation | 2013-04-02 | 5 | 18 | 15
21 | Insulation Inspection | 2013-04-09 | 1 | 20 | 15
22 | Rough MEP | 2013-01-01 | 0
23 | Rough Heating | 2013-03-07 | 2 | 18 | 22
24 | Rough Plumbing | 2013-03-07 | 3 | 18 | 22
25 | Install Furnace | 2013-03-11 | 1 | 19 | 22
26 | 1st Plumbing Inspection | 2013-03-12 | 3 | 20 | 22
27 | Rough Electric | 2013-03-22 | 5 | 24 | 22
28 | Permanent Power | 2013-03-29 | 1 | 25 | 22
29 | 1st Electric Inspection | 2013-03-29 | 1 | 25 | 22
30 | Heating and Framing Inspection | 2013-04-01 | 1 | 27 | 22
31 | Interior Finish | 2013-01-01 | 0
32 | Drywall | 2013-04-10 | 12 | 30 | 31
33 | Trim Delivery | 2013-04-26 | 1 | 32 | 31
34 | Garage Door | 2013-04-26 | 1 | 32 | 31
35 | Interior Paint | 2013-04-26 | 6 | 32 | 31
36 | Trim Labor | 2013-05-06 | 3 | 35 | 31
37 | Cabinet Installation | 2013-05-06 | 7 | 35 | 31
38 | Final Plumbing | 2013-05-15 | 2 | 37 | 31
39 | Final Electric | 2013-05-17 | 2 | 38 | 31
40 | 2nd Plumbing Inspection | 2013-05-21 | 3 | 39 | 31
41 | 2nd Electrical Inspection | 2013-05-24 | 1 | 40 | 31
42 | Closeout | 2013-01-01 | 0
43 | Punch Out | 2013-05-27 | 1 | 41 | 42
44 | Walk Through | 2013-05-30 | 1 | 43 | 42
45 | 3rd Electrical Inspection | 2013-05-30 | 1 | 43 | 42
46 | Sign Off | 2013-05-31 | 1 | 44 | 42
47 | Final Inspection | 2013-05-31 | 1 | 45 | 42
48 | Closing | 2013-06-03 | 3 | 47 | 42